## FlexeraOne
Environments | Required? | Implementation Task |  |  | Estimate (days) | Total
Dev | Yes | FNMS System Design |  |  | 5 | 5
Test | No | FNMS Systems
QA/PreProd | No |  | 2 | FNMS System (Cloud) | 2 | 4
Prod | Yes |  | 4 | Beacons | 0.5 | 2
|  |  | 1 | RDS Inventory | 15 | 15
|  |  | 3 | Custom Business Adapters | 1 | 3
Extra Features | Required? |  | 2 | Custom Reports | 0.5 | 1
M365 | Yes |  | 2 | Extra Features |  | 2
Azure | Yes | Vendor Onboarding
AWS | No |  | 3 | Teir-1 Vendors |  | 30
Oracle | No |  | 5 | Teir-2 Vendors |  | 15
SAP | No | Inventory Imports and Data Quality |  |  | 15 | 15
RSD | Yes
|  | Sub-Total (days) |  |  |  | 92
FlexeraOne |  | Enterprise Overheads |  |  | 10% | 9
|  | Project Management |  |  | 10% | 9
DS Smith |  | Total (days) |  |  |  | 110
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This kind of organisation can take a lot of work to get the design fully worked
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Complex custom inventory adapter needs to be developed

## Weighting
Environments | Required? | Points |  |  | Factor | Value |  | Beacons
Dev | Yes | 1 |  |  | Number of Isolated Networks | 1 |  | 4
Test | No | 0 |  |  | Total Number of Devices | 24000
QA/PreProd | No | 0
Prod | Yes | 1
| 2 | 2
Extra Features | Required? | Points | Days |  | Enterprise Factor | InScope | Value | Points
M365 | Yes | 1 | 0.5 |  | Bank, Financial, or Government? | No | 0.2 | 0
Azure | Yes | 1 | 0.5 |  | Large Enterprise? (>50k devices) | Yes | 0.1 | 0.1
AWS | No | 0 | 0 |  | Agile Project Methodology? | No | 0.2 | 0
RDS | Yes | 1 | 0.5 |  |  |  |  | 0
|  | 0 | 0 |  |  |  |  | 0
|  | 3 | 2 |  |  |  |  | 0.1
TEIR-1 Vendor | Required | Points | Estimate | Days
Microsoft | Yes | 1 | 10 | 10
IBM | Yes | 1 | 10 | 10
Oarcle | Yes | 1 | 10 | 10
SAP | No | 0 | 30 | 0
|  | 0 | 0 | 0
|  | 3 |  | 30
TEIR-2 Vendor | Required | Points | Estimate | Days
vendor1 | Yes | 1 | 3 | 3
vendor2 | Yes | 1 | 3 | 3
vendor3 | Yes | 1 | 3 | 3
vendor4 | Yes | 1 | 3 | 3
vendor5 | No | 0 | 3 | 0
|  | 4 |  | 12
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of required Beacons = the number of isolated networds in PROD + 1 extra Beacon for every 10K devices + 1 Beacon for every non-PROD environment

## Lookup
Required?
Yes
No